## Project Plan
TAG |  | Deliverable |  |  | Dependency |  | Responsible | Intermediate Targets |  | Status/Comments | Final | Status/Comments
| 0 | Administration |  |  | From | To | Blantz | Draft | Next |  | Complete
| 0 | Deliverables Outline |  |  |  |  | Blantz |  | 2000-12-12 |  | 2001-05-11
| 0 | Agenda for Vancouver |  |  |  |  | Blantz |  | 2001-01-12 |  | 2001-02-12
| 0 | Develop CC section for TA document |  |  |  | TA | Shreve | 2000-11-22
| 0 | Develop BP section for TA document |  |  |  | TA | Riemer/Clark | 2000-12-15 |  |  | 2000-12-22
| 0 | Develop acceptance criteria |  |  |  |  | Blantz | 2000-12-18 | 2000-12-22 | Rough to Anne/Paul 12/18 | 2001-01-14
| 0 | Develop Change Control procedures |  |  |  |  | Blantz | 2000-12-18 | 2000-12-22 | Rough to Anne/Paul 12/18 | 2001-01-14
| 0 | Joint Delivery Team Web Site |  |  |  |  | Hayes/Whittle
| 0 | Issues List
| 1 | Context/Metamodel/Extension |  |  |  |  | Adcock
1A | 1 | Implementation Model Methodology |  |  | 5A,5B,5D | QR | Adcock | 2000-11-10 |  |  | 2001-02-23
1B | 1 | CC Extension Methodology for Context |  |  |  | 5A,1G | Adcock | 2000-11-08 |  |  | 2001-02-07
1C | 1,4 |  |  | Incorporate CC Context | 4D |  | Bryan |  |  |  | 2001-02-07
1D | 1 | Core Component Context |  |  |  | 1G | Gregory | 2000-11-08 |  |  | 2001-02-07
1E | 1 |  | Matrix |  |  |  | Gregory | 2000-11-10 |  |  | 2-Feb-01`
1F | 1 |  | Value Classifications |  |  | RR | Gregory | 2000-11-10 |  |  | 2-Feb-01`
1G | 1,2 | Registration Requirements |  |  | 1B,1D,1G |  | Bryan | 2000-12-15 |  |  | 2001-02-12
| 2 | Discovery/Analysis/Draft Design Rules |  |  |  |  | Shreve |  |  |  | 2001-02-16
2A | 2 | CC Discovery Methodology |  |  |  | 3A/QR | Adcock | 2000-11-09 | 2001-01-01 |  | 2001-02-09
2B | 2 | CC Extension Rules for Context |  |  |  | 3A,1G | Adcock |  | 2000-12-15 |  | 2001-02-09
2C | 2 | Method for specifying Core Components |  |  |  |  | Sugamata | 2000-07-15 | 2000-12-15 |  | 2001-02-09
2C1 |  | Naming Conventions |  |  |  |  | Probert | 2000-10-27 | 2000-12-15 |  | 2001-02-09
2D | 2 | Matrix of Representation Classes |  |  |  | 3F | Probert | 2000-11-01 | 2000-12-15 |  | 2001-02-09
2F | 2,5 | Dictionary of Core Components |  |  | 5E,5G | RR | Heilig | 2000-12-12 | 2000-01-14 | Comments due back 1/10/01 | 2001-02-09
2H | 2 | Industry Analysis Results |  |  |  |  | Heilig |  | 2000-12-11 | Continue at X12 | 2001-01-01
2I | 2,3 | Update CC entry form |  |  |  |  | Bryan |  |  |  |  | Done, updates as required
2J | 2 | Registration of Elements |  |  |  |  | Schultz |  |  |  | 2001-02-16
2K | 1,2 | Registration Requirements |  |  |  | RR | Bryan | 2000-12-15 |  |  | 2-Feb-01`
| 3 | Domain Teams |  |  |  |  | Blantz
3A | 3 | Top-to-bottom example |  |  |  |  | Blantz |  | 2001-02-09 | Materials Management | 2001-02-28
3B | 3 | Use Discovery Methodology |  |  |  |  | Blantz |  | 2001-02-09 | Start at X12 | 2001-02-16
3C | 3 | Use guidelines and template to |  |  | 5A,5B |  | Blantz |  | 2001-02-09 | Start at X12 | 2001-02-16
3D | 3 |  | Prove the methodologies |  |  |  | Blantz |  | 2001-02-09 | Start at X12 | 2001-02-16
3E | 3 |  | Validate the Comm Trans pattern |  |  |  | Blantz |  | 2001-02-09 | Start at X12 | 2001-02-16
3F | 3 | Review Representation Classes |  |  |  |  | Blantz | 2000-11-07 | 2000-12-22 | Should be the final | 2000-12-22
3G | 3 | Review Naming Conventions |  |  |  |  | Blantz | 2000-11-07 | 2000-12-22 | Should be the final | 2000-12-22
3H | 3 | Meta level desc of POC demo for Vancouver |  |  |  | POC | Handelman | 2000-11-27 |  | Manufacturing | 2000-11-27 | Manufacturing
3I | 3 | Publication of demo CC specs |  |  |  | POC | Handelman |  |  | Manufacturing | 2001-01-15 | Manufacturing
| 4 | Metamodel |  |  |  |  | Levine
4A | 4 | Infrastructure Specification Schema |  |  |  | QR/TP | Riemer | 2000-11-30 |  | Incorporate CC Context | 2000-12-22 | On track
4B | 4 |  | Specification schema in UML |  | 4C |  | Clark | 2000-11-30 | 2000-12-11 | Parallel | 2000-12-22
4C | 4 |  | Specification schema in XML |  | 4B |  | Dubray/Casanave | 2000-11-30 | 2000-12-15 | Parallel | 2000-12-22
4D | 4 |  | UML to XML production rules |  |  |  | Casanave | 2000-11-08 |  |  | 2000-12-22
4E | 4 |  | Set of interaction patterns |  |  |  | Clark | 2000-11-08 |  |  | 2000-12-22
4F | 4 |  | Common model element for patterns |  |  |  | Clark | 2000-12-06 | 2000-12-13 |  | 2000-12-22
4G | 4 |  | Mapping of the DTD to TP |  |  |  | Lonjon | 2000-12-06 | 2000-12-15 |  | 2000-12-22
4H | 4 |  | Specification document 4B thru 4G |  |  |  | Riemer/Clark |  |  |  | 2000-12-22
4I | 4 |  | Examples - one big, one small |  |  |  | McC/Casa |  | 2000-12-20 | Automotive work | 2000-12-22
4J | 4 |  |  | Business description |  |  | McC/Casa |  | 2000-12-15 | Common Bus Process Alignment | 2000-12-22
4K | 4 |  |  | XML Document |  |  | McC/Casa |  | 2000-12-20 | Automotive work | 2000-12-22
4L | 4 | Scenarios for use of metamodel |  |  |  |  | Riemer | 2000-11-15 | 2001-01-14 |  | 2001-01-31
| 5 | Common Business Processes |  |  |  |  | Levine | 2000-11-10 |  |  | 2000-12-29
5A | 5 | Guidelines for applying methodology end to end |  |  |  | QR | Hayes | 2000-11-08 |  | This deliverable is required to provide instructions and rationale for completing the ebXML BP Worksheets | 2001-02-17 | New draft
5B | 5 |  | Business Process Specification Template |  |  |  | Hayes | 2000-11-10 | 17 Feb. | Reviewed by Domain | 2001-02-17 | Appendix to the BP Guidelines
5C | 5 | Align with outside methodologies |  |  |  |  | Clark | 2000-04-03 |  | How can specifications for business collaboration developed outside ebXML be utilized in the ebXML infrastructure? | Ongoing
5D | 5 | ebXML Business Process Worksheets |  |  |  | QR | Welsh | 2000-11-10 | 2001-01-31 | Step-by-step procedure for applying UMM | 2001-02-17
5E | 5,2 | Catalog of Common Business Processes |  |  | 2F | QR | Sharma | 2000-11-10 | 2001-02-17 |  | Ongoing
5G | 5 | Update Common Business Process Documents |  |  |  |  | Welsh | 2000-11-11 | 2001-02-17 | Specifications of common business processes listed in the catalog | Ongoing | Part of the Catalog of Common Business Processes
5H | 5 | eCommerce Patterns |  |  |  | QR | Haugen | 2000-11-01 | 2001-01-31 | Business collaboration patterns to be submitted to QR to raise awareness of this document | 2001-02-17
5I | 5 | POC Example | [8 empty] | 2000-11-30
5J | 5 |  | Materials Management example |  |  |  | Clark | 2000-11-30 | 2000-11-30 | Mataerials management example document completed for review prior to and at ebXML Tokyo
5K | 5 |  | Business Process Editor | [6 empty] | Vancouver Lunch & Learn based on a collaboration scenario
5L | 5 |  | World Ordering Collaboration Scenario |  |  |  | Clark
5M | 5 | ebXML Metamodel |  |  |  | QR | Clark |  |  |  | 2001-02-17

## Help
Help
The deliverables worksheet is a simple database of the deliverables, the corresponding status, file names, and a few other things. The worksheet can be used to keep the current and previous information on the deliverables. It is used to create the Deliverables web page for the CC/BP Joint Delivery Team website. The web page is created by selecting Create Web Page on the Tools menu.
The basic steps are as follows:
1. Update worksheet and save
2. Create the web page (Tool menu --> Create Web Page)
3. FTP the web page and this file to www.ebxml.org (user name "jdt").
The web page will be created in the c:\temp\ directory of your hard drive. The default file name will be "deliverables.html" FTP this web page to the appropriate directory on your web site (e.g. http://www.ebxml.org/project_teams/jdt/).
Tool Properties/Configuration
To change the tool properties, select Edit Create Web Page Properties on the Tools menu.
Deliverables file name - This is the web page that contains the links to the deliverables. The default is deliverables.html.
Directory - The default directory that the web page is written to is C:\TEMP\.
Data Input Notes:
TAG - Set this to an appropriate value from the TAG column in the Schedule worksheet. The worksheet is sorted first by this TAG and then by Deliverable Title and then by Date.
Deliverable Title - Provide an appropriate title for the deliverable. Be sure to use the same spelling of the title each time.
Status - Choose any statuses that you would like. Recommended statuses include, but are not limited to: Work-In-Progress, DRAFT, In Quality Review, Approved Standard. If you do not provide a status, the status will be displayed as UNKNOWN.
Date -The date associated with the Status. If you do not provide a date, the date will be displayed as UNKNOWN.
File Name - Name of the file associated with the deliverable, if any.
URL - The URL of the file associated with the deliverable, if any. The URL must include the file name as the macro is not smart enough to figure it out from the URL. JDT deliverables can be placed into the http://www.ebxml.org/project_teams/jdt/ts/ directory.
Comment - Any comment. Must be less than 255 characters.

## deliverables
TAG | Deliverable Title | Status | Date | File Name | URL | Comment
0A | JDT Project Plan v 10.3 | Work-In-Progress | 2001-01-14 | BPCC_Deliverables_v10.3.xls | http://www.ebxml.org/project_teams/business_process/jdt/BPCC_Deliverables_v10.3.xls
4A | ebXML Business Process Specification Schema Version 0.87 | In Quality Review | 2001-01-01 | SpecificationSchemaQR0.87.zip | http://www.ebxml.org/project_teams/jdt/ts/SpecificationSchemaQR0.87.zip
5A | ebXML Business Process Methodology Guidelines | Work-In-Progress | 2000-10-30 | eMethodologyGuidelinesV0_3a.pdf | http://www.ebxml.org/project_teams/business_process/wip/ccbp-analysis/eMethodologyGuidelinesV0_3a.pdf | Item on hold pending outcome of Worksheet based approach.
5B | Business Process Specification Template | Work-In-Progress | 2000-11-11 | BPSpecTemplate_WIP_0_5.zip | http://www.ebxml.org/project_teams/business_process/wip/ccbp-analysis/BPSpecTemplate_WIP_0_5.zip | Needs to be updated to reflect the latest Metamodel and UMM (TMWGN090).
5I | POC Example (Materials Management MetaModel Example) | Complete | 2000-11-30 | mmx | http://www.ebxml.org/project_teams/business_process/wip/ccbp-analysis/mmx/
5P | ebXML Business Process Editor Toolset Proof Of Concept | Submitted | 2000-12-20 | Business Process Editor Toolset POC Proposal REVISED.doc | http://www.ebxml.org/project_teams/business_process/ccbp-analysis/Business%20Process%20Editor%20Toolset%20POC%20Proposal%20REVISED.doc
5P | Business Collaboration Protocol Specification &amp; Implementation Proof Of Concept | Submitted | 2000-12-13 | Collaboration POC Proposal.doc | http://www.ebxml.org/project_teams/business_process/ccbp-analysis/Collaboration%20POC%20Proposal.doc

## __properties (hidden)
Property | Value | Description
DeliverablesFileName | deliverables.html
OutputDirectory | C:\TEMP\ | Directory to create the web page. Must have a trailing \. E.g. c:\temp\
Contact1 | Mary Kay Blantz
ContactMailto1 | mblantz@netfish.com
Contact2 | Paul Levine
ContactMailto2 | plevine@telcordia.com